## Executive Dashboard
CLOUDSHIELD TECHNOLOGIES : GRC EXECUTIVE DASHBOARD
Cybersecurity Risk & Compliance Assessment ¦ Independent Portfolio Project ¦ Elizabeth Kapusa
KPI | Value | Residual Rating | Count
Total Risks | 5 | Low | 0
High Residual Risks | 4 | Medium | 1
Medium Residual Risks | 1 | High | 4
Open Findings | 5 | Critical | 0
Executive Risk Narrative
CloudShield’s initial assessment identifies concentrated risk in privileged identity management, vulnerability remediation, and third-party governance. The most urgent actions are to close privileged-access gaps, enforce MFA for privileged interactive accounts, remediate the overdue production vulnerability, and formalize repeatable evidence-based control processes. Backup restoration testing is a moderate but important resilience gap.
NIST CSF 2.0 Current vs. Target Posture
Assessment Method
The portfolio uses a 1–4 implementation scale (1 Initial, 2 Developing, 3 Defined, 4 Managed) to compare CloudShield's current practices with its target state. This is an assessment aid created for the simulated project and is not presented as a NIST CSF Tier.

## Risk Register
CLOUDSHIELD TECHNOLOGIES: CYBERSECURITY RISK REGISTER
Independent GRC Portfolio Project ¦ Simulated Organization ¦ Prepared by Elizabeth Kapusa ¦ 2026
Risk ID | Risk / Finding | Business Asset | Threat Scenario / Control Gap | Likelihood | Impact | Inherent Score | Inherent Rating | Existing Controls | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Treatment | Risk Owner | Recommended Remediation | Status | Target Date
GRC-001 | Inadequate Privileged Account Offboarding | Azure production infrastructure / privileged identities | Former engineer's privileged Azure account remained active for 19 days after termination; three successful post-termination authentications; no formal quarterly privileged-access review. | 4 | 4 | 16 | High | Microsoft 365 account disabled on termination date; HR termination record exists; Azure sign-in logging enabled. | 4 | 4 | 16 | High | Mitigate | IT / Security Manager | Automate HR-to-IT offboarding; revoke all access immediately at termination; maintain privileged-account inventory; perform recurring privileged-access reviews; alert on anomalous/post-termination access. | Open | 2026-11-06
GRC-002 | Incomplete MFA Enforcement for Privileged Accounts | Azure privileged identities | Two privileged administrative/service accounts are not covered by the standard MFA requirement. | 4 | 4 | 16 | High | MFA is enabled for most user accounts; privileged roles are identifiable in Azure. | 4 | 4 | 16 | High | Mitigate | Identity & Access Management Owner | Require MFA for all eligible privileged interactive accounts; use appropriate workload identities for service accounts; remove unnecessary privilege; document exceptions and recurring access reviews. | Open | 2026-10-30
GRC-003 | Overdue Production Vulnerability / No Remediation SLA | Internet-facing customer application | A high-severity vulnerability has remained unresolved for 47 days and no formal severity-based remediation SLA exists. | 4 | 4 | 16 | High | Vulnerability scanning is performed and the issue has been identified. | 4 | 4 | 16 | High | Mitigate | Application / Security Engineering | Remediate the identified vulnerability; adopt Critical=24-hour and High=7-day targets; require documented exceptions, compensating controls, accountable risk acceptance, and overdue escalation. | Open | 2026-10-13
GRC-004 | Inadequate Backup Restoration Testing | PostgreSQL customer database | Daily backups complete successfully, but no documented restoration test has been performed for 11 months. | 3 | 4 | 12 | High | Daily automated backups, retention, documented backup procedure, and a previously successful restoration test. | 2 | 4 | 8 | Medium | Mitigate | Infrastructure / Business Continuity Owner | Perform and document restoration testing at least quarterly; record recovery results, RTO/RPO observations, failures, evidence, and corrective actions. | Open | 2026-11-30
GRC-005 | Inadequate Third-Party Security Review | Customer information shared with SaaS vendor | Vendor was approved two years ago, but there is no documented annual security review, current questionnaire, or current assurance report on file. | 4 | 4 | 16 | High | Vendor onboarding approval exists and only limited customer information is shared. | 4 | 4 | 16 | High | Mitigate | Vendor Risk / Security Owner | Establish annual risk-based vendor reviews; obtain current security questionnaire and assurance evidence; document risk decisions, contractual requirements, exceptions, and remediation tracking. | Open | 2026-11-20

## Risk Matrix
5 × 5 CYBERSECURITY RISK MATRIX
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5
Score | Rating
1–4 | Low
5–9 | Medium
10–16 | High
17–25 | Critical

## Evidence Tracker
AUDIT EVIDENCE & REMEDIATION TRACKER
Risk ID | Evidence Requested | Evidence Status | Testing Result | Finding / Observation | Remediation Owner | Due Date | Remediation Status | Retest Required | Notes
GRC-001 | HR termination record; M365 disable timestamp; Azure account status; Azure sign-in logs; privileged role assignment; access-review records | Partial | Fail | Azure privileged access remained active 19 days after termination; three successful authentications occurred. | IT / Security Manager | 2026-11-06 | Open | Yes | No customer-data access or alteration has been established.
GRC-002 | Privileged account inventory; role assignments; MFA/authentication methods; conditional-access configuration; exception records | Partial | Fail | Two privileged accounts are outside standard MFA enforcement. | Identity & Access Management Owner | 2026-10-30 | Open | Yes | Service accounts should be evaluated for workload identity/non-interactive design.
GRC-003 | Vulnerability scan report; ticket history; asset criticality; exception approvals; remediation standard | Partial | Fail | High-severity internet-facing vulnerability remains open after 47 days; no formal SLA. | Application / Security Engineering | 2026-10-13 | Open | Yes | Proposed SLA: Critical 24 hours; High 7 days.
GRC-004 | Backup job logs; retention settings; restoration-test records; recovery procedure | Partial | Needs Improvement | Backups complete, but restoration capability has not been documented/tested in 11 months. | Infrastructure / Business Continuity Owner | 2026-11-30 | Open | Yes | Quarterly documented restoration testing recommended.
GRC-005 | Vendor inventory; security questionnaire; assurance report; contract security clauses; annual review record | Insufficient | Fail | No current annual vendor security review or assurance evidence on file. | Vendor Risk / Security Owner | 2026-11-20 | Open | Yes | Annual risk-based vendor reassessment recommended.

## NIST CSF Assessment
CLOUDSHIELD TECHNOLOGIES — NIST CSF 2.0 CURRENT vs. TARGET ASSESSMENT
Portfolio assessment scale: 1 Initial ¦ 2 Developing ¦ 3 Defined ¦ 4 Managed — project scoring aid, not a NIST CSF Tier.
Function | Category / Focus | Current State Evidence | Key Gap | Current Score | Target Score | Gap | Priority | Linked Risk(s) | Recommended Action | Assessment Status
GOVERN | Risk Management Strategy & Policy | Security activities and some procedures exist, but risk decisions and remediation expectations are not consistently formalized. | No unified cybersecurity risk methodology, formal risk acceptance workflow, or complete policy/SLA structure. | 2 | 4 | 2 | High | GRC-003 | Approve a documented cyber-risk methodology, risk acceptance process, control ownership model, and vulnerability-remediation standard. | Gap Identified
GOVERN | Cybersecurity Supply Chain Risk Management | A SaaS vendor was approved during onboarding and only limited customer information is shared. | No documented annual reassessment, current security questionnaire, or current assurance evidence. | 1 | 4 | 3 | High | GRC-005 | Establish risk-tiered vendor due diligence, annual reassessment, contractual security requirements, evidence retention, and remediation tracking. | Gap Identified
IDENTIFY | Asset & Risk Understanding | Major cloud assets, customer application, PostgreSQL database, privileged identities, and vendors are identifiable; vulnerability scanning is performed. | Asset/risk information is not yet managed through a consistent enterprise risk-register ownership process. | 2 | 4 | 2 | Medium | GRC-001; GRC-003; GRC-005 | Maintain authoritative inventories, assign accountable owners, and review the risk register on a defined cadence. | Improvement Needed
PROTECT | Identity Management, Authentication & Access Control | MFA protects most user accounts; M365 access was disabled on termination date; Azure sign-in logs and privileged role data are available. | Two privileged accounts are outside standard MFA enforcement; a terminated user's privileged Azure access remained active for 19 days. | 1 | 4 | 3 | High | GRC-001; GRC-002 | Automate joiner/mover/leaver workflows, enforce MFA for privileged interactive accounts, use workload identities, and conduct recurring privileged-access reviews. | Gap Identified
PROTECT | Platform Security & Vulnerability Remediation | Vulnerability scanning is performed and the high-severity production issue was identified. | No formal remediation SLA; high-severity internet-facing vulnerability remained unresolved for 47 days. | 2 | 4 | 2 | High | GRC-003 | Implement Critical=24-hour and High=7-day remediation targets, exception/risk-acceptance workflow, compensating controls, and overdue escalation. | Gap Identified
DETECT | Continuous Monitoring & Event Analysis | Azure sign-in logging exists and post-termination authentications can be identified; vulnerability scanning is also in place. | No demonstrated mature alerting/escalation process for anomalous privileged access. | 2 | 4 | 2 | Medium | GRC-001; GRC-002 | Define high-risk identity alerts, triage/escalation ownership, retention expectations, and recurring review. | Improvement Needed
RESPOND | Incident Management & Analysis | CloudShield can investigate authentication logs and has incident-response procedures. | Procedures have not been tested recently; no demonstrated exercise/evidence package for the privileged-access scenario. | 2 | 4 | 2 | Medium | GRC-001 | Run a tabletop exercise, define incident severity/escalation criteria, preserve evidence, and track lessons learned. | Improvement Needed
RECOVER | Recovery Planning & Execution | Daily PostgreSQL backups complete successfully; backups are retained; procedures exist; a prior restoration test succeeded. | No documented restoration test has been performed for 11 months. | 2 | 4 | 2 | Medium | GRC-004 | Perform documented restoration tests at least quarterly; record results, RTO/RPO observations, failures, and corrective actions. | Improvement Needed

## Dashboard Data
Residual Rating | Count | Function | Current | Target
Low | 0 | GOVERN | 1.5 | 4
Medium | 1 | IDENTIFY | 2 | 4
High | 4 | PROTECT | 1.5 | 4
Critical | 0 | DETECT | 2 | 4
|  | RESPOND | 2 | 4
|  | RECOVER | 2 | 4